## INSTRUCTIONS
Section | Instruction
General Use | Do not rename, move, or delete any existing tabs.
Only input data in cells that have blue text.
Use drop-downs where provided to ensure consistent data entry.
Update the file monthly as needed to keep dashboard data accurate.
Blue Text Fields | Blue text indicates a a cell for data to be entered.
Editing Guidance | Do not remove rows with formulas. Add new rows at the bottom of the tables.
Data Format | Use MM/DD/YYYY format for all dates. Ensure consistent spelling for trade names and status types. Date needs to be first of the month to pull data.
Backup Reminder | Save a backup of the file before major updates. Use version control in the file name if necessary.
Dashboard Tab | The dashboard is read-only. All charts and KPIs auto-populate from the other tabs. Do not manually enter data in this tab.
Schedule Tab | Enter Critical path items only! Include progress, upcoming look-ahead items, and any delays.
Safety Tab | Record toolbox talks, standdowns, incidents, weekend/OT work, and site visits (DOB, FDNY, OSHA).
Risks Tab | Use this tab to track key project risks, including scope gaps, outstanding decisions, coordination issues, or external dependencies. For each item, define the risk, assess its impact, outline the mitigation strategy, assign an owner, and update the status
Quality Tab | Log top issues by trade, open days, benchmark inspections, and NCRs. Include resolution strategy.
RFIs & Submittals Tab | Track RFIs and Submittals. Log RFI number, description, status, submission and response dates. Use "Open", "Closed", or "Overdue" for status tracking.
Financials Tab | Input actual costs, projected costs, and budget vs actuals. GC/GR variance tracking is automated.
Scorecard Tab | Use this tab to evaluate overall project health using a weighted scoring system across key performance indicators, including financials, schedule, safety, and reporting. Input each category's score based on defined metrics, and update regularly to monitor performance trends. Include client satisfaction survey results below to track feedback and engagement
SECTION | RESPONSIBILITY | CONTRIBUTOR
Dashboard | Read Only. Ask Administrator
Wins | PM | Superintendent & Foremen
Schedule | PM | Superintendent & Foremen
Risks | PM | Superintendent & Foremen
Safety | PM | Superintendent & Foremen
Quality | PM | Superintendent & Foremen
Submittals & RFIs | PM | Superintendent & Foremen
Financial | QS/Estimator | PM & Project Accountant
Scorecard Calc | PM & Marketing | PM & Marketing

## DASHBOARD
Monthly Progress Report | [26 empty] | #VALUE!
2025-05-01
WINS (REALIZED) |  | SCHEDULE | [20 empty] | FINANCIAL
Approved by Client
| Topped Out Superstructure |  |  |  | Start | Finish | MTM Delta |  |  | Rev # | [13 empty] | Original Contract Amt. |  | 8800000 | MTM DELTA
|  |  |  | Contract | 2025-01-09 | 2026-05-07 | 0 |  |  |  |  | STATUS SUMMARY | CRITICAL DELAYS / VARIANCES |  | RECOVERY PLAN |  | FORECAST IMPACT |  |  | NOTES / ACTION ITEMS |  |  |  | Current Contract Amt. |  | 9116960.48 | 1.139%
|  |  |  | Baseline | 2025-01-08 | 2026-06-25 | 0 | 🔴 N |  | Rev#1 | [13 empty] | Variance |  | 3.602%
|  |  |  | Currently Tracking | 2025-01-08 | 2026-06-25 | 0 |  |  |  |  | 🔴 At Risk | [List specific issues: e.g., delayed delivery, inspections, manpower shortage] |  | [Explain steps being taken: e.g., OT, resequencing, adding crews] |  | [Impact to key milestones or turnover] |  |  | [Escalations, decisions needed, risks to monitor] |  |  |  | Pending CO's |  | 84328.46 | -64.11%
[24 empty] | Contingency Remaining |  | N/A
|  |  |  | Actual | 2025-01-08 | TBD | TBD |  |  |  |  | 🔴 At Risk | [List specific issues: e.g., delayed delivery, inspections, manpower shortage] |  | [Explain steps being taken: e.g., OT, resequencing, adding crews] |  | [Impact to key milestones or turnover] |  |  | [Escalations, decisions needed, risks to monitor] |  |  |  | Billed this Month |  | $400,000.0 / 4.4%
| Major Submittals Approved (Window Wall, Porcelain, Doors) | [22 empty] | Total Billed |  | $2,997,804.2 / 32.9%
|  |  |  | 49 | 0 days | Warning, provide Recovery Plan | [5 empty] | 🟡 Behind | Delayed delivery |  | [Explain steps being taken: e.g., OT, resequencing, adding crews] |  | [Impact to key milestones or turnover] |  |  | [Escalations, decisions needed, risks to monitor] |  |  |  | Total Paid |  | $2,683,097.5 / 29.4%
|  |  |  | Contract | Baseline |  | AVG Daily Manpower | [16 empty] | Remaining Balance |  | $6,433,863.0 / 70.6%
|  |  |  | COMPLETION VARIANCE |  |  | Sub 1 |  |  | 0 |  | 🔴 At Risk | mapower |  | [Explain steps being taken: e.g., OT, resequencing, adding crews] |  | [Impact to key milestones or turnover] |  |  | [Escalations, decisions needed, risks to monitor] |  |  |  | Retainage |  | $127,441.6 / 1.4%
|  |  |  | 40% |  | Warning, provide Recovery Plan | Sub 2 |  |  | 0 | [13 empty] | Cost to Complete |  | $6,786,492.3 / 74.4%
|  |  |  | CRITICAL MISSED STARTS |  |  | Sub 3 |  |  | 0 |  | 🟢 On Track | manpower |  | [Explain steps being taken: e.g., OT, resequencing, adding crews] |  | [Impact to key milestones or turnover] |  |  | [Escalations, decisions needed, risks to monitor]
| No accidents |  |  | 74.86% |  |  | Sub 4 |  |  | 0 | [15 empty] | 1
|  |  |  | PROJECT % COMPLETE |  |  | Sub 5 |  |  | 0 | [15 empty] | AGE OF OLDEST UNAPPROVED CO
95%
RISK BOUGHT OUT
|  | RISKS (Ranked by Severity) | [23 empty] | 1
AGING BALANCE
| Quickly Rescinded PSWO |  | RISK DESCRIPTION | [6 empty] | IMPACT |  | MITIGATION STRATEGY | [6 empty] | OWNER |  | STATUS |  |  |  |  | 8.8182
|  |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🟢 Complete |  |  |  |  | AVG. DAYS FOR PAYMENT RECEIVED
|  |  | Access Agreements with Neighbors | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🟡 Planned |  |  |  | Profitability is Margin fade but no plan
< 50% = 🔴 Bad Cash Position
|  |  | Trades to award: | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🟡 In Progress |  |  | 🟢 Y |  | MONTH END CLOSED OUT
[24 empty] | 🔴 N |  | PROCORE FORECASTING IN LINE W/SCHEDULE
FOCUS AREAS (UPCOMING MTH) |  |  | Kitchen Cabinet Design | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🟢 Complete |  |  | 🔴 N |  | MONITORED RESOURCES UPDATED
| Topped Out Superstructure |  | Kitchen Cabinet Design | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🔴 Not Started |  |  |  | Budget | Forecast | Spent to Date / % | Status
[24 empty] | GR's | 299746.97 | 89149.77 | $15,000.00 / 5.0% | 🔴 Over Budget
|  |  | Kitchen Cabinet Design | [6 empty] | 🔴 High |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🔴 Not Started |  |  | GC's | 850018.69 | 323265.39 | $20,000.00 / 2.4% | 🟢 On Track
|  |  | Kitchen Cabinet Design | [6 empty] | ⚪ Low |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🔴 Not Started |  |  |  |  | 44 / 107% | 112.5
[26 empty] | This Period / MTM Delta | Total to Date
| Major Submittals Approved (Window Wall, Porcelain, Doors) |  | Kitchen Cabinet Design | [6 empty] | 🟡 Medium |  | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | [6 empty] | Dir. of Construction |  | 🔴 Not Started |  |  |  |  | OT HOURS
CRITICAL SUBMITTALS & RFIS
SAFETY
| No accidents |  | TIMEFRAME |  | CATEGORY |  | DESCRIPTION/ACTIVITY |  |  |  | STATUS |  | NOTES/OUTCOME/ACTION |  |  | RESPONSIBLE |  | 4,635 / 9.7% |  |  | 114231
|  |  | Lookback |  | Toolbox Talk – Scheduled |  | Scaffold Overbuild |  |  |  | 🟢 Completed |  | Signed off, executed per plan |  |  | Asst. Super |  | This Period / MTM Delta |  |  | Total to Date
TOTAL HOURS WORKED
|  |  | Lookback |  | Notable Visitor – FDNY |  | Fall Protection |  |  |  | 🟡 Scheduled |  | 28 attendees, good feedback from field |  |  | Dir. of Construction |  | 0 |  |  | 1
[18 empty] | This Period |  |  | Total to Date
|  |  | Lookback |  | Notable Visitor – FDNY |  | Heat Stress Awareness |  |  |  | 🟡 Scheduled |  | Held after near miss, all trades participated |  |  | Dir. of Construction |  | RECORDABLE INCIDENTS
| Quickly Rescinded PSWO | [16 empty] | 17 / -29.2% |  |  | 120
|  |  | Lookback |  | Notable Visitor – FDNY |  | OSHA Informal Walkthrough |  |  |  | 🟡 Scheduled |  | No citations, documented for record |  |  | Dir. of Construction |  | This Period / MTM Delta |  |  | Total to Date
TOTAL ORIENTATIONS
|  |  | Lookback |  | Notable Visitor – FDNY |  | Concrete Pour – Foundation |  |  |  | 🟡 Scheduled |  | AHV secured, no issues during extended shift |  |  | Dir. of Construction |  | 1000 |  |  | 1
[18 empty] | $ VALUE |  |  | Total Open
VIOLATIONS
SCORECARD |  | QUALITY
| PROJECT SCORECARD |  | 17 |  | 77 | 0 | 0 |  | TIMEFRAME |  | CATEGORY |  |  | DESCRIPTION |  |  |  |  | TRADE |  | STATUS | OUTCOME / COMMENTS |  |  |  | RESPONSIBLE | ACTION PLAN
| 59% |  | This Period |  | Total to Date | This Period | Total to Date |  | Lookback |  | Quality – High-Risk Observation |  |  | Uneven tile in Unit 405 |  |  |  |  | TileCo |  | 🔴 Open | Pending rework |  |  |  | Dir. of Construction | Schedule crew for rework
|  |  | OBSERVATIONS |  |  | PUNCHLIST |  |  | Lookback |  | Benchmark – Completed |  |  | Tile Mockup |  |  |  |  | TileCo |  | 🟢 Passed | Signed off by owner |  |  |  | Dir. of Construction | None
|  |  | 1 |  | 2 | 3 | 4 |  | Lookahead |  | Benchmark – Scheduled |  |  | Millwork Mockup |  |  |  |  | LMN Millwork |  | 🟡 Scheduled | Pending consultant date |  |  |  | Dir. of Construction | Confirm samples / setup review
|  |  | AVG. DAYS PAST DUE |  | AVG. DAYS TO CLOSE | AVG. DAYS PAST DUE | AVG. DAYS TO CLOSE |  | Lookback |  | Delivery – Rejected |  |  | HVAC Unit delivery damaged |  |  |  |  | MechSupplyCo |  | 🔴 Rejected | Unit returned to vendor |  |  |  | Dir. of Construction | Replacement arriving 6/25
|  |  | MAIN OFFENDERS |  |  | MAIN OFFENDERS |  |  | Lookahead |  | Commissioning – Upcoming |  |  | ERV Air Balancing |  |  |  |  | DEF Mech |  | 🟡 Scheduled | Coordination with MEP team |  |  |  | Dir. of Construction | Confirm balancing crew
| CLIENT SATISFACTION FROM: ANONYMOUS |  | STNY |  |  | STNY |  |  | Lookback |  | Inspection – Special |  |  | Concrete Cylinder Break Test |  |  |  |  | Atlas Eng |  | 🟢 Passed | Compressive strength verified |  |  |  | Dir. of Construction | None
| 60% |  | ABM |  |  | ABM |  |  | Lookback |  | Inspection – NCR |  |  | Failed weld at base plate |  |  |  |  | SteelCo |  | 🔴 NCR | Reweld scheduled 6/27 |  |  |  | Dir. of Construction | Reinspection on 6/28
|  |  | TRYSLER |  |  | TRYSLER |  |  | Lookback |  | Inspection – NCR |  |  | Failed weld at base plate |  |  |  |  | SteelCo |  | 🔴 NCR | Reweld scheduled 6/28 |  |  |  | Dir. of Construction | Reinspection on 6/29
|  |  | TRYSLER |  |  | TRYSLER |  |  | Lookback |  | Inspection – NCR |  |  | Failed weld at base plate |  |  |  |  | SteelCo |  | 🔴 NCR | Reweld scheduled 6/29 |  |  |  | Dir. of Construction | Reinspection on 6/30
|  |  | TRYSLER |  |  | TRYSLER |  |  | Lookback |  | Inspection – NCR |  |  | Failed weld at base plate |  |  |  |  | SteelCo |  | 🔴 NCR | Reweld scheduled 6/30 |  |  |  | Dir. of Construction | Reinspection on 6/31
Note on AU4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date needs to be first of the month to pull data.

## WINS
WINS (REALIZED)
WIN # | DESCRIPTION (TEXT NEEDS TO FIT IN THE COLUM WIDTH AND HEIGHT)
WIN 1 | Topped Out Superstructure
WIN 2 | Major Submittals Approved (Window Wall, Porcelain, Doors)
WIN 3 | No accidents
WIN 4 | Quickly Rescinded PSWO
FOCUS AREAS (UPCOMING MTH)
WIN # | DESCRIPTION (TEXT NEEDS TO FIT IN THE COLUM WIDTH AND HEIGHT)
FA 1 | Topped Out Superstructure
FA 2 | Major Submittals Approved (Window Wall, Porcelain, Doors)
FA 3 | No accidents
FA 4 | Quickly Rescinded PSWO

## SCHEDULE
TASK | CONTRACT START | CONTRACT FINISH | BASELINE START | BASELINE FINISH | CURRENT START | CURRENT FINISH | ACTUAL START | ACTUAL FINISH | START VARIANCE | FINISH VARIANCE | INSTRUCTIONS FOR USE
Project Milestones (Start & Finish) | 2025-01-09 | 2026-05-07 | 2025-01-08 | 2026-06-25 | 2025-01-08 | 2026-06-25 | 2025-01-08 | 2025-03-24 |  |  | 1. FIRST ROW IS LOCKED 2. ALL BLANKS CELL SHOULD RECEIVE AN NA 3. THE LAST LINE ON THIS TABLE SHOULD NEVER BE DELETED AND SHOULD ALWAYS BE SUB COMPLETETION 4. NEVER HAVE ANY BLANK ROWS
Critical Path Item 1 | 2025-01-09 | 2025-01-15 | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | 0 | 0
Critical Path Item 2 | 2025-01-09 | 2025-02-06 | 2025-02-11 | 2025-02-11 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 29 | 29
Critical Path Item 3 | 2025-02-07 | 2025-02-13 | 2025-02-19 | 2025-02-19 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 33 | 33
Critical Path Item 4 | 2025-02-07 | 2025-02-13 | 2025-02-19 | 2025-02-19 | 2025-03-24 | 2025-03-24 | 2025-02-19 | 2025-02-19 | 0 | 33
Critical Path Item 5 | 2025-05-15 | 2025-05-15 | 2025-04-11 | 2025-04-11 | 2025-06-16 | 2025-06-20 | NA | NA |  | 70
Critical Path Item 6 | NA | NA | 2025-07-22 | 2025-07-22 | 2025-09-19 | 2025-09-19 | NA | NA |  | 59
Critical Path Item 7 | 2025-08-25 | 2025-08-25 | 2025-10-08 | 2025-10-08 | 2025-12-29 | 2025-12-29 | NA | NA |  | 82
Critical Path Item 8 | 2026-05-14 | 2026-05-07 | 2026-05-12 | 2026-05-12 | 2025-12-29 | 2025-12-29 | NA | NA |  | -134
Critical Path Item 9 | 2026-06-11 | 2026-05-07 | 2026-06-25 | 2026-06-25 | 2026-04-30 | 2026-04-30 | NA | NA |  | -56
Contractural Substaintial Completion [DO NOT DELETE THIS LINE] | 2025-01-09 | 2026-05-07 | 2025-01-09 | 2026-06-25 | 2025-01-09 | 2026-06-25 | NA | NA |  | 0
|  | Baseline Approved by Client |  | 🔴 N
|  | Baseline Revision |  | Rev#1
This Month |  | 2026-05-07 |  | 2026-06-25 |  | 2026-06-25 |  | NA
Previous Month (Paste Special values) |  | 2026-05-07 |  | 2026-06-25 |  | 2026-06-25 |  |  | *Manually Input last months values. If first month reporting enter same value as this month.
MTM Change |  | 0 |  | 0 |  | 0 |  | TBD
AVERAGE Daily Manpower
Company Name | Avg Daily over past 30 days
Sub 1 | 0
Sub 2 | 0
Sub 3 | 0
Sub 4 | 0
Sub 5 | 0
SCHEDULE ITEM | STATUS SUMMARY | CRITICAL DELAYS / VARIANCES | RECOVERY PLAN | FORECAST IMPACT | NOTES / ACTION ITEMS
PRIORITY ITEM 1 | 🔴 At Risk | [List specific issues: e.g., delayed delivery, inspections, manpower shortage] | [Explain steps being taken: e.g., OT, resequencing, adding crews] | [Impact to key milestones or turnover] | [Escalations, decisions needed, risks to monitor]
PRIORITY ITEM 2 | 🔴 At Risk | [List specific issues: e.g., delayed delivery, inspections, manpower shortage] | [Explain steps being taken: e.g., OT, resequencing, adding crews] | [Impact to key milestones or turnover] | [Escalations, decisions needed, risks to monitor]
PRIORITY ITEM 3 | 🟡 Behind | Delayed delivery | [Explain steps being taken: e.g., OT, resequencing, adding crews] | [Impact to key milestones or turnover] | [Escalations, decisions needed, risks to monitor]
PRIORITY ITEM 4 | 🔴 At Risk | mapower | [Explain steps being taken: e.g., OT, resequencing, adding crews] | [Impact to key milestones or turnover] | [Escalations, decisions needed, risks to monitor]
PRIORITY ITEM 5 | 🟢 On Track | manpower | [Explain steps being taken: e.g., OT, resequencing, adding crews] | [Impact to key milestones or turnover] | [Escalations, decisions needed, risks to monitor]
INSTRUCTIONS FOR USE
Status Summary should be brief but clear (e.g., "Behind due to facade delay", "On track post weather recovery"). Recovery Plan is critical if you’re off track—list actionable steps, not just “monitoring.” Forecast Impact should tie directly to milestone changes or risk to turnover date.
Formulas:
CONTRACT START = +MIN([CONTRACT START, row below]:D14)
CONTRACT FINISH = +MAX([CONTRACT FINISH, row below]:E14)
BASELINE START = +MIN([BASELINE START, row below]:F14)
BASELINE FINISH = +MAX([BASELINE FINISH, row below]:G14)
CURRENT START = +MIN([CURRENT START, row below]:H14)
CURRENT FINISH = +MAX([CURRENT FINISH, row below]:I14)
ACTUAL START = +MIN([ACTUAL START, row below]:J14)
ACTUAL FINISH = +MAX([ACTUAL FINISH, row below]:K14)

## RISKS
RISK # | RISK DESCRIPTION | IMPACT | MITIGATION STRATEGY | OWNER | STATUS
RISK 1 | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🟢 Complete
RISK 2 | Access Agreements with Neighbors | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🟡 Planned
RISK 3 | Trades to award: | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🟡 In Progress
RISK 4 | Kitchen Cabinet Design | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🟢 Complete
RISK 5 | Kitchen Cabinet Design | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🔴 Not Started
RISK 6 | Kitchen Cabinet Design | 🔴 High | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🔴 Not Started
RISK 7 | Kitchen Cabinet Design | ⚪ Low | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🔴 Not Started
RISK 8 | Kitchen Cabinet Design | 🟡 Medium | Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders Outstanding Change Orders | Dir. of Construction | 🔴 Not Started

## SAFETY
MONTH # | MONTH | HOURS WORKED THIS PERIOD | RECORDABLE INCIDENTS THIS PERIOD | ORIENTATIONS THIS PERIOD |  | VLN # | VLN Description | VLN Value | Status | VLN Value / Status
Month 1 | 2025-01-01 | 862 | 0 | 20 |  | 1 |  | 0 | Open | 0
Month 2 | 2025-02-01 | 1924 | 0 | 23 |  | 2 |  | 1000 | Open | 1000
Month 3 | 2025-03-01 | 2585 | 0 | 36 |  | 3 |  | 0 | Open | 0
Month 4 | 2025-04-01 | 4226 | 1 | 24 |  | 4 |  | 0 | Open | 0
Month 5 | 2025-05-01 | 4635 | 0 | 17 |  | 5 |  | 0 | Open | 0
Month 6 | 2025-06-01 | 99999 | 0 | 0 |  | 6 |  | 0 | Open | 0
Month 7 | 2025-07-01 | 0 | 0 | 0 |  | 7 |  | 0 | Open | 0
Month 8 | 2025-08-01 | 0 | 0 | 0 |  | 8 |  | 0 | Open | 0
Month 9 | 2025-09-01 | 0 | 0 | 0 |  | 9 |  | 0 | Open | 0
Month 10 | 2025-10-01 | 0 | 0 | 0 |  | 10 |  | 0 | Open | 0
Month 11 | 2025-11-01 | 0 | 0 | 0 |  | 11 |  | 0 | Open | 0
Month 12 | 2025-12-01 | 0 | 0 | 0 |  | 12 |  | 0 | Open | 0
Month 13 | 2026-01-01 | 0 | 0 | 0 |  | 13 |  | 0 | Open | 0
Month 14 | 2026-02-01 | 0 | 0 | 0 |  | 14 |  | 0 | Open | 0
Month 15 | 2026-03-01 | 0 | 0 | 0 |  | 15 |  | 0 | Open | 0
Month 16 | 2026-04-01 | 0 | 0 | 0 |  | 16 |  | 0 | Open | 0
Month 17 | 2026-05-01 | 0 | 0 | 0 |  | 17 |  | 0 | Open | 0
Month 18 | 2026-06-01 | 0 | 0 | 0 |  | 18 |  | 0 | Open | 0
Month 19 | 2026-07-01 | 0 | 0 | 0 |  | 19 |  | 0 | Open | 0
Month 20 | 2026-08-01 | 0 | 0 | 0 |  | 20 |  | 0 | Open | 0
Month 21 | 2026-09-01 | 0 | 0 | 0 |  | 21 |  | 0 | Open | 0
Month 22 | 2026-10-01 | 0 | 0 | 0 |  | 22 |  | 0 | Open | 0
Month 23 | 2026-11-01 | 0 | 0 | 0 |  | 23 |  | 0 | Open | 0
Month 24 | 2026-12-01 | 0 | 0 | 0
Month 25 | 2027-01-01 | 0 | 0 | 0 |  | Total | 0 | 1000 |  | 1000
Month 26 | 2027-02-01 | 0 | 0 | 0
Month 27 | 2027-03-01 | 0 | 0 | 0
Month 28 | 2027-04-01 | 0 | 0 | 0
Month 29 | 2027-05-01 | 0 | 0 | 0
Month 30 | 2027-06-01 | 0 | 0 | 0
TOTAL |  | 114231 | 1 | 120
TIMEFRAME | CATEGORY | DESCRIPTION/ACTIVITY | STATUS | NOTES/OUTCOME/ACTION | RESPONSIBLE
Lookback | Toolbox Talk – Scheduled | Scaffold Overbuild | 🟢 Completed | Signed off, executed per plan | Asst. Super
Lookback | Notable Visitor – FDNY | Fall Protection | 🟡 Scheduled | 28 attendees, good feedback from field | Dir. of Construction
Lookback | Notable Visitor – FDNY | Heat Stress Awareness | 🟡 Scheduled | Held after near miss, all trades participated | Dir. of Construction
Lookback | Notable Visitor – FDNY | OSHA Informal Walkthrough | 🟡 Scheduled | No citations, documented for record | Dir. of Construction
Lookback | Notable Visitor – FDNY | Concrete Pour – Foundation | 🟡 Scheduled | AHV secured, no issues during extended shift | Dir. of Construction
Formulas:
MONTH = EOMONTH([MONTH, row above],0)+1

## QUALITY
MONTH # | MONTH | OBSERVATIONS THIS PERIOD | PUNCHLIST ITEM THIS PERIOD
Month 1 | 2025-01-01 | 0 | 0
Month 2 | 2025-02-01 | 0 | 0
Month 3 | 2025-03-01 | 36 | 0
Month 4 | 2025-04-01 | 24 | 0
Month 5 | 2025-05-01 | 17 | 0
Month 6 | 2025-06-01 | 0 | 0
Month 7 | 2025-07-01 | 0 | 0
Month 8 | 2025-08-01 | 0 | 0
Month 9 | 2025-09-01 | 0 | 0
Month 10 | 2025-10-01 | 0 | 0
Month 11 | 2025-11-01 | 0 | 0
Month 12 | 2025-12-01 | 0 | 0
Month 13 | 2026-01-01 | 0 | 0
Month 14 | 2026-02-01 | 0 | 0
Month 15 | 2026-03-01 | 0 | 0
Month 16 | 2026-04-01 | 0 | 0
Month 17 | 2026-05-01 | 0 | 0
Month 18 | 2026-06-01 | 0 | 0
Month 19 | 2026-07-01 | 0 | 0
Month 20 | 2026-08-01 | 0 | 0
Month 21 | 2026-09-01 | 0 | 0
Month 22 | 2026-10-01 | 0 | 0
Month 23 | 2026-11-01 | 0 | 0
Month 24 | 2026-12-01 | 0 | 0
Month 25 | 2027-01-01 | 0 | 0
Month 26 | 2027-02-01 | 0 | 0
Month 27 | 2027-03-01 | 0 | 0
Month 28 | 2027-04-01 | 0 | 0
Month 29 | 2027-05-01 | 0 | 0
Month 30 | 2027-06-01 | 0 | 0
Month 31 | 2027-07-01 | 0 | 0
TOTAL |  | 77 | 0
| Column1 | OBSERVATIONS | PUNCHLIST
| AVG. DAYS PAST DUE | 1 | 3
| AVG. DAYS TO CLOSE | 2 | 4
RANGE BY ASCENDING OFFENCES | MAIN OFFENDER 1 (SUB NAME) | STNY | STNY
| MAIN OFFENDER 2 | ABM | ABM
| MAIN OFFENDER 3 | TRYSLER | TRYSLER
| MAIN OFFENDER 4 | TRYSLER | TRYSLER
| MAIN OFFENDER 5 | TRYSLER | TRYSLER
TIMEFRAME | CATEGORY | DESCRIPTION | TRADE | STATUS | OUTCOME / COMMENTS | RESPONSIBLE | ACTION PLAN
Lookback | Quality – High-Risk Observation | Uneven tile in Unit 405 | TileCo | 🔴 Open | Pending rework | Dir. of Construction | Schedule crew for rework
Lookback | Benchmark – Completed | Tile Mockup | TileCo | 🟢 Passed | Signed off by owner | Dir. of Construction | None
Lookahead | Benchmark – Scheduled | Millwork Mockup | LMN Millwork | 🟡 Scheduled | Pending consultant date | Dir. of Construction | Confirm samples / setup review
Lookback | Delivery – Rejected | HVAC Unit delivery damaged | MechSupplyCo | 🔴 Rejected | Unit returned to vendor | Dir. of Construction | Replacement arriving 6/25
Lookahead | Commissioning – Upcoming | ERV Air Balancing | DEF Mech | 🟡 Scheduled | Coordination with MEP team | Dir. of Construction | Confirm balancing crew
Lookback | Inspection – Special | Concrete Cylinder Break Test | Atlas Eng | 🟢 Passed | Compressive strength verified | Dir. of Construction | None
Lookback | Inspection – NCR | Failed weld at base plate | SteelCo | 🔴 NCR | Reweld scheduled 6/27 | Dir. of Construction | Reinspection on 6/28
Lookback | Inspection – NCR | Failed weld at base plate | SteelCo | 🔴 NCR | Reweld scheduled 6/28 | Dir. of Construction | Reinspection on 6/29
Lookback | Inspection – NCR | Failed weld at base plate | SteelCo | 🔴 NCR | Reweld scheduled 6/29 | Dir. of Construction | Reinspection on 6/30
Lookback | Inspection – NCR | Failed weld at base plate | SteelCo | 🔴 NCR | Reweld scheduled 6/30 | Dir. of Construction | Reinspection on 6/31
Formulas:
MONTH = EOMONTH([MONTH, row above],0)+1

## SUBMITTALS & RFI
Trade | Open Critical RFIs | Open Critical Submittals
Electrical | 8 | 3
HVAC | 5 | 2
Windows | 4 | 5
Metals | 4 | 5
Foundation | 4 | 5
Existing Conditions | 4 | 5
Metals | 4 | 5
Conveying Equipment | 4 | 5
Exterior Improvements | 4 | 5
| 0 | 0
| 0 | 0

## FINANCIALS
DESCRIPTION | THIS PERIOD | LAST PERIOD | & DIF
Original Contract Amt. | 8800000
Current Contract Amt. | 9116960.48 | 9014313 | 1.139%
Pending CO's | 84328.46 | 234983 | -64.11%
Age of oldest unapproved CO | 1 | 1 | 0%
Profitability | Margin fade but no plan | Within Range |  |  | Based on the original financial projection
Cash Position | < 50% = 🔴 Bad Cash Position | < 50% = 🔴 Bad Cash Position |  |  | ≥ 100% = 🟢 Good Cash Position; 50% – 99% = 🟡 Medium / Watch Zone; < 50% = 🔴 Bad Cash Position; Metric Cash Collected = $2,000,000 AR Outstanding = $400,000 Remaining Forecasted Cost = $1,500,000 Cash Position % = ($2,000,000 + $400,000) ÷ $1,500,000 × 100 = 160%
Remaining in Contingency | N/A | N/A
Total Billed | 2997804.23 | 2344355.7 | 27.87%
Bill This Pay Period | 400000
Total Paid | 2683097.46 | 1960036.58 | 36.89%
Remaining Balance | 6433863.02 | 6669957.3 | -3.54%
Retainage | 127441.56 | 97614.85 | 30.56%
Cost to Complete | 6786492.26 | 6717008.18 | 1.034%
MONTH | BUDGET | FORECAST | SPENT TO DATE2 | STATUS |  | Variance (Budget - Actual) | RAG Status | Meaning
General Requirements | 299746.97 | 89149.77 | 15000 | 🔴 Over Budget |  | ≥ 0% | 🟢 On Track / Positive | Under or exactly on budget (great)
General Conditions | 850018.69 | 323265.39 | 20000 | 🟢 On Track |  | -0.01% to -5% | 🟡 Watch | Slight overrun, monitor
[6 empty] | > -5% | 🔴 Over Budget | Significant overrun, needs correction
MONTH # | MONTH | INVOICE SENT | INVOICE PAID | DELTA |  | MONTH # | MONTH | OT HOURS WORKED THIS PERIOD
Month 1 | 2025-11-01 | 2024-11-07 | 2024-11-14 | 7 |  | Month 1 | 2025-01-01 | 12
Month 2 | 2025-12-01 | 2024-11-20 | 2024-12-02 | 12 |  | Month 2 | 2025-02-01 | 18
Month 3 | 2026-01-01 | 2024-12-20 | 2024-12-31 | 11 |  | Month 3 | 2025-03-01 | 18
Month 4 | 2026-02-01 | 2025-01-31 | 2025-01-31 | 0 |  | Month 4 | 2025-04-01 | 21
Month 5 | 2026-03-01 | 2025-03-03 | 2025-03-06 | 3 |  | Month 5 | 2025-05-01 | 43.5
Month 6 | 2026-04-01 | 2025-03-03 | 2025-03-07 | 4 |  | Month 6 | 2025-06-01
Month 7 | 2026-05-01 | 2025-03-25 | 2025-04-02 | 8 |  | Month 7 | 2025-07-01
Month 8 | 2026-06-01 | 2025-03-25 | 2025-04-16 | 22 |  | Month 8 | 2025-08-01
Month 9 | 2026-07-01 | 2025-04-25 | 2025-05-02 | 7 |  | Month 9 | 2025-09-01
Month 10 | 2026-08-01 | 2025-04-25 | 2025-05-13 | 18 |  | Month 10 | 2025-10-01
Month 11 | 2026-09-01 | 2025-05-29 | 2025-06-03 | 5 |  | Month 11 | 2025-11-01
Month 12 | 2026-10-01 |  |  |  |  | Month 12 | 2025-12-01
Month 13 | 2026-11-01 |  |  |  |  | Month 13 | 2026-01-01
Month 14 | 2026-12-01 |  |  |  |  | Month 14 | 2026-02-01
Month 15 | 2027-01-01 |  |  |  |  | Month 15 | 2026-03-01
Month 16 | 2027-02-01 |  |  |  |  | Month 16 | 2026-04-01
Month 17 | 2027-03-01 |  |  |  |  | Month 17 | 2026-05-01
Month 18 | 2027-04-01 |  |  |  |  | Month 18 | 2026-06-01
Month 19 | 2027-05-01 |  |  |  |  | Month 19 | 2026-07-01
Month 20 | 2027-06-01 |  |  |  |  | Month 20 | 2026-08-01
Month 21 | 2027-07-01 |  |  |  |  | Month 21 | 2026-09-01
Month 22 | 2027-08-01 |  |  |  |  | Month 22 | 2026-10-01
Month 23 | 2027-09-01 |  |  |  |  | Month 23 | 2026-11-01
Month 24 | 2027-10-01 |  |  |  |  | Month 24 | 2026-12-01
Month 25 | 2027-11-01 |  |  |  |  | Month 25 | 2027-01-01
Month 26 | 2027-12-01 |  |  |  |  | Month 26 | 2027-02-01
Month 27 | 2028-01-01 |  |  |  |  | Month 27 | 2027-03-01
Month 28 | 2028-02-01 |  |  |  |  | Month 28 | 2027-04-01
Month 29 | 2028-03-01 |  |  |  |  | Month 29 | 2027-05-01
Month 30 | 2028-04-01 |  |  |  |  | Month 30 | 2027-06-01
TOTAL |  |  |  | 8.8182 |  | TOTAL |  | 112.5
CURRENTAGING BALANCE |  |  |  | 1
PROJECT BUYOUT
Total Trade Costs Budgeted |  | 200000000
Total Trade Costs Committed (Use budget dollar value) |  | 190000001
% Bought out |  | 95%
COST MANAGEMENT
MONTH END CLOSED OUT |  |  | 🟢 Y
PROCORE FORECASTING IN LINE W/SCHEDULE |  |  | 🔴 N
MONITORED RESOURCES UPDATED BASED ON ACTUALS |  |  | 🔴 N
Formulas:
THIS PERIOD = EOMONTH([THIS PERIOD, row above],0)+1
RAG Status = EOMONTH([RAG Status, row above],0)+1

## SCORECARD CALC
PROJECT SCORE
DESCRIPTION | SCORE | METRICS | PROJECT SCORE | WEIGHTING | OVERALL SCORE
Accounts Receivable | 3 | < 45 | 3 | 12% | 12%
| 2 | 46-60
| 0 | 61-75
Profitability | 3 | Within Range | 0 | 12% | 0%
| 2 | Out of Range, but has a plan
| 0 | Margin fade but no plan
Cash Position | 3 | ≥ 100% | 0 | 12% | 0%
| 2 | 50% – 99%
| 0 | < 50%
Change Orders (Avg Days Open) | 3 | < 45 | 3 | 8% | 8%
| 2 | 46-60
| 0 | 61-75
Safety incidents | 3 | No Incidents | 3 | 14% | 14%
| 2 | < 1 Incidents
| 0 | 2+ Incidents
Schedule Performance (Critcal Missed Starts) | 3 | <5% | 3 | 15% | 15%
| 2 | 6-9%
| 0 | 10%+
Completion Variance | 3 | 0 or - Days | 0 | 15% | 0%
| 2 | 1-14 Days
| 0 | 15+ Days
Observations (Avg Days Open) | 3 | <5 Days | 3 | 10% | 10%
| 2 | 6-10 Days
| 0 | 11+
Daily Reports (# of reports not complete and distributed on Same Day) | 3 | <2 | 0 | 2% | 0%
| 2 | 3-4 |  |  |  | MANUAL INPUT
| 0 | 5+
59%
CLIENT SATISFACTION
WHO WAS SURVEYED: | ANONYMOUS |  |  | MANUAL INPUT
QUESTIONS | SCORE (1 to 5)
Q1 | 3
Q2 | 3
Q3 | 3 |  |  | MANUAL INPUT
Q4 | 3
Q5 | 3
Q6 | 3
60%

## DROPDOWN
RISKS TAB |  |  | SCHEDULE |  |  | SAFETY |  |  | QUALITY |  | SUBMITTALS & RFIS | FINANCIAL
IMPACTS | OWNER | STATUS | STATUS SUMMARY | APPROVED | REVISION | TIMEFRAME | CATEGORY | STATUS | CATEGORY | STATUS | TRADES | FORECAST | APPROVED | APPROVED | PROFITABILITY
🔴 High | Scheduler | 🔴 Not Started | 🟢 On Track | 🟢 Y | Rev#1 | Lookback | High-Risk Item – Completed | 🟢 Completed | Quality – High-Risk Observation | 🔴 Open | Existing Conditions | 🟢 On Track | 🟢 Y | ≥ 100% = 🟢 Good Cash Position | Within Range
🟡 Medium | PM | 🟡 Planned | 🟡 Behind | 🔴 N | Rev#2 | Lookahead | High-Risk Item – Upcoming | 🟢 Positive | Benchmark – Completed | 🟢 Passed | Concrete | 🟡 Watch | 🔴 N | 50% – 99% = 🟡 Medium / Watch Zone | Out of Range, but has a plan
⚪ Low | Asst. Super | 🟡 In Progress | 🔴 At Risk |  | Rev#3 |  | Toolbox Talk – Completed | 🟡 Scheduled | Benchmark – Scheduled | 🟡 Scheduled | Foundation | 🔴 Over Budget |  | < 50% = 🔴 Bad Cash Position | Margin fade but no plan
| Asst. PM | 🟢 Complete |  |  | Rev#4 |  | Toolbox Talk – Scheduled | 🟡 Planned | Mockup – Completed | 🔴 Rejected | Superstructure
| Super |  |  |  | Rev#5 |  | Safety Standdown – Completed | 🔴 High Risk | Mockup – Scheduled | 🟡 Scheduled | Masonry
| Senior PM |  |  |  | Rev#6 |  | Safety Standdown – Scheduled | 🔴 Delayed | Delivery – Rejected | 🟢 Passed | Metals
| PX |  |  |  | Rev#7 |  | Weekend/OT Work – Completed |  | Delivery – Upcoming | 🔴 NCR | Drywall & Carpentry
| Dir. of Construction |  |  |  | Rev#8 |  | Weekend/OT Work – Planned |  | Commissioning – Completed |  | Roofing
| Principal |  |  |  | Rev#9 |  | Notable Visitor – DOB |  | Commissioning – Upcoming |  | Millwork
[5 empty] | Rev#10 |  | Notable Visitor – FDNY |  | Inspection – Special |  | Finishes
[5 empty] | Rev#11 |  | Notable Visitor – Client |  | Inspection – NCR |  | Specialties
[7 empty] | Notable Visitor – OSHA |  |  |  | Equipment
[7 empty] | Notable Visitor – Other |  |  |  | Doors & Frames
[7 empty] | Safety Win – Team Performance |  |  |  | Glass & Glazing
[7 empty] | Safety Win – Milestone with No Incidents |  |  |  | Conveying Equipment
[7 empty] | Safety Win – Inspection Success |  |  |  | Sprinkler
Plumbing
HVAC
Building Automation Systems
Electrical
Low Voltage
Utilities
Painting
Flooring
Self Levelling
Windows
Lighting
Exterior Improvements